## Assumptions
Assumptions & Planning Basis
ID | Assumption
A1 | Plan baseline date: Monday 2026-07-13. Source TASKS.md is dated July 2024; all completed work is treated as pre-baseline history.
A2 | Capacity: 1 primary FTE per workstream, 6 productive hours/day, 30 h/week, Mon-Fri, no holidays modelled.
A3 | Statuses derived from checkboxes: [x] = Done, [ ] = Not start. No evidence of In-progress/Blocked in source; the Status column supports all four values for ongoing tracking.
A4 | Priorities: assigned by the plan for open work (GitLab CI = High since it is the target stack; Jenkins = Low, descope candidate). Completed tasks default to Medium (retrospective, informational only).
A5 | Effort: estimates for completed tasks are retrospective reconstructions; Actual = Estimate is assumed for them. Open-work estimates are bottom-up by sub-task count and complexity.
A6 | Effort is tracked at Task level; sub-task rows intentionally leave effort blank to avoid double counting in roll-ups.
A7 | Task 9.4 does not exist in the source file (numbering gap preserved as-is).
A8 | PIC roles (DevOps Engineer, SDET) are placeholders pending staffing; QA Architect = IQ142.
A9 | Phase 11 tasks are proposed AI-driven enhancements added by this plan (from the 'Next Steps' backlog + architect recommendations); they require sponsor approval before commit.
A10 | Gantt charts open work only (Phase 9 + Phase 11) plus milestones; completed phases 1-8 & 10 are listed in Task Plan as baseline.
A11 | Dependencies 'M1/M2' denote milestone predecessors. 11.5 requires CI history, hence depends on M1.

## Executive Dashboard
Executive Dashboard - AI-Driven Test Automation Framework v2.0
Baseline: 2026-07-13 ¦ Scope: Playwright + Behave + Allure + AI (Ollama) framework ¦ Source: TASKS.md
Total Tasks | Done | In-progress | Not start | Blocked | % Complete (tasks) | Est Hours (total) | Hours Remaining | % Complete (hours) | Target GA
43 | 29 | 0 | 14 | 0 | 67.44% | 480 | 283 | 41.04% | 2026-10-16
Phase Progress | [7 empty] | Milestones
Phase | Tasks | Done | % Done | Est (h) | Remaining (h) | Status |  | ID | Milestone | Target
P1 Environment Setup | 3 | 3 | 100% | 8 | 0 | Complete |  | M1 | CI/CD Live (GitLab primary, all providers green) | 2026-08-04
P2 Project Structure Setup | 2 | 2 | 100% | 5 | 0 | Complete |  | M2 | AI v2 Core Complete (healing v2, multi-model, gen, triage) | 2026-09-08
P3 Core Framework Implementation | 2 | 2 | 100% | 14 | 0 | Complete |  | M3 | AI Analytics & Quality Insights Live | 2026-09-25
P4 AI Integration Implementation | 4 | 4 | 100% | 42 | 0 | Complete |  | M4 | Framework v2.0 GA | 2026-10-16
P5 Test Implementation | 3 | 3 | 100% | 32 | 0 | Complete
P6 Reporting Setup | 2 | 2 | 100% | 6 | 0 | Complete
P7 Testing and Validation | 4 | 4 | 100% | 16 | 0 | Complete
P8 Advanced Features | 7 | 7 | 100% | 64 | 0 | Complete
P9 CI/CD Integration | 4 | 0 | 0% | 71 | 71 | Not start
P10 Documentation | 2 | 2 | 100% | 10 | 0 | Complete
P11 AI-Driven Enhancements (Proposed) | 10 | 0 | 0% | 212 | 212 | Not start
Top Risks & Mitigations
ID | Risk | Impact | Likelihood | Mitigation
R1 | Single FTE per workstream; absence delays critical path (9.5->9.2->M1) | High | Medium | Cross-train SDET on CI scripts; keep 9.1/9.3 parallelizable
R2 | Jenkins infrastructure availability unconfirmed | Medium | High | Task 9.3 marked Low priority / descope candidate; decision by M1
R3 | AI healing applies wrong selector silently in expanded coverage (11.1) | High | Medium | >=90% confidence gate + post-heal assertion + healing telemetry
R4 | LLM cost growth as AI features expand | Medium | Medium | 11.2 cost guardrails: local-first routing, token budgets, rule-based fallback
R5 | Generated tests (11.3) erode suite quality | Medium | Medium | Mandatory human review gate, Gherkin lint, duplicate detection

## Task Plan
Task Plan - Full Decomposition
Parsed from TASKS.md (statuses stripped and re-derived). Effort at Task level only (A6).
ID | Phase | Task Name | Sub-task Name | Level | Status | Priority | Est (h) | Actual (h) | PIC | Predecessor | Successor | Start | End | Note
1.1 | P1 Environment Setup | Create Virtual Environment |  | Task | Done | Medium | 2 | 2 | QA Architect (IQ142) |  |  |  |  | Completed pre-baseline (3 sub-tasks)
1.1 | P1 Environment Setup | Create Virtual Environment | Create Python virtual environment | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
1.1 | P1 Environment Setup | Create Virtual Environment | Activate virtual environment | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
1.1 | P1 Environment Setup | Create Virtual Environment | Upgrade pip to latest version | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
1.2 | P1 Environment Setup | Install Dependencies |  | Task | Done | Medium | 4 | 4 | QA Architect (IQ142) |  |  |  |  | Completed pre-baseline (7 sub-tasks)
1.2 | P1 Environment Setup | Install Dependencies | Install Playwright | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
1.2 | P1 Environment Setup | Install Dependencies | Install Behave | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
1.2 | P1 Environment Setup | Install Dependencies | Install Allure Behave adapter | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
1.2 | P1 Environment Setup | Install Dependencies | Install Playwright browsers | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
1.2 | P1 Environment Setup | Install Dependencies | Install PyYAML for configuration | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
1.2 | P1 Environment Setup | Install Dependencies | Install Ollama for AI models | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
1.2 | P1 Environment Setup | Install Dependencies | Remove BehaveX dependency (not needed) | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
1.3 | P1 Environment Setup | Create Requirements File |  | Task | Done | Medium | 2 | 2 | QA Architect (IQ142) |  |  |  |  | Completed pre-baseline (4 sub-tasks)
1.3 | P1 Environment Setup | Create Requirements File | Create `requirements.txt` with all dependencies | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
1.3 | P1 Environment Setup | Create Requirements File | Verify all packages are listed correctly | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
1.3 | P1 Environment Setup | Create Requirements File | Remove unnecessary dependencies | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
1.3 | P1 Environment Setup | Create Requirements File | Add Ollama dependency for AI integration | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
2.1 | P2 Project Structure Setup | Create Directory Structure |  | Task | Done | Medium | 3 | 3 | QA Architect (IQ142) |  |  |  |  | Completed pre-baseline (10 sub-tasks)
2.1 | P2 Project Structure Setup | Create Directory Structure | Create `features/` directory for Gherkin files | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
2.1 | P2 Project Structure Setup | Create Directory Structure | Create `steps/` directory for step definitions | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
2.1 | P2 Project Structure Setup | Create Directory Structure | Create `pages/` directory for Page Object Model | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
2.1 | P2 Project Structure Setup | Create Directory Structure | Create `ai/` directory for AI integration | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
2.1 | P2 Project Structure Setup | Create Directory Structure | Create `playwright_config/` directory for browser setup | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
2.1 | P2 Project Structure Setup | Create Directory Structure | Create `reports/` directory for Allure reports | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
2.1 | P2 Project Structure Setup | Create Directory Structure | Create `helpers/` directory for utility functions | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
2.1 | P2 Project Structure Setup | Create Directory Structure | Create `utils/` directory for framework utilities | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
2.1 | P2 Project Structure Setup | Create Directory Structure | Create `resources/` directory for project resources | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
2.1 | P2 Project Structure Setup | Create Directory Structure | Ensure all directories exist and are properly organized | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
2.2 | P2 Project Structure Setup | Configure Behave |  | Task | Done | Medium | 2 | 2 | QA Architect (IQ142) |  |  |  |  | Completed pre-baseline (3 sub-tasks)
2.2 | P2 Project Structure Setup | Configure Behave | Create `behave.ini` configuration file | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
2.2 | P2 Project Structure Setup | Configure Behave | Set default tags to exclude skipped tests | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
2.2 | P2 Project Structure Setup | Configure Behave | Configure output format | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
3.1 | P3 Core Framework Implementation | Create Browser Setup |  | Task | Done | Medium | 6 | 6 | QA Architect (IQ142) |  |  |  |  | Completed pre-baseline (4 sub-tasks)
3.1 | P3 Core Framework Implementation | Create Browser Setup | Create `utils/playwright_config/browser_setup.py` | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
3.1 | P3 Core Framework Implementation | Create Browser Setup | Implement browser launch functionality | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
3.1 | P3 Core Framework Implementation | Create Browser Setup | Add page creation methods | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
3.1 | P3 Core Framework Implementation | Create Browser Setup | Include browser cleanup methods | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
3.2 | P3 Core Framework Implementation | Implement Environment Hooks |  | Task | Done | Medium | 8 | 8 | QA Architect (IQ142) |  |  |  |  | Completed pre-baseline (9 sub-tasks)
3.2 | P3 Core Framework Implementation | Implement Environment Hooks | Create `environment.py` file | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
3.2 | P3 Core Framework Implementation | Implement Environment Hooks | Implement `before_all()` hook for browser setup | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
3.2 | P3 Core Framework Implementation | Implement Environment Hooks | Implement `after_all()` hook for cleanup | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
3.2 | P3 Core Framework Implementation | Implement Environment Hooks | Add error handling for browser operations | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
3.2 | P3 Core Framework Implementation | Implement Environment Hooks | Test browser initialization | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
3.2 | P3 Core Framework Implementation | Implement Environment Hooks | Add headless mode support via environment variables | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
3.2 | P3 Core Framework Implementation | Implement Environment Hooks | Add browser selection support via environment variables | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
3.2 | P3 Core Framework Implementation | Implement Environment Hooks | Integrate Page Object Model factory | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
3.2 | P3 Core Framework Implementation | Implement Environment Hooks | Integrate AI Selector Healer initialization | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
4.1 | P4 AI Integration Implementation | AI Selector Healer Core |  | Task | Done | Medium | 16 | 16 | QA Architect (IQ142) |  |  |  |  | Completed pre-baseline (7 sub-tasks)
4.1 | P4 AI Integration Implementation | AI Selector Healer Core | Create `ai/selector_healer.py` with AISelectorHealer class | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
4.1 | P4 AI Integration Implementation | AI Selector Healer Core | Implement Ollama integration with devstral:24b model | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
4.1 | P4 AI Integration Implementation | AI Selector Healer Core | Add screenshot capture functionality for AI analysis | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
4.1 | P4 AI Integration Implementation | AI Selector Healer Core | Implement HTML content extraction for AI context | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
4.1 | P4 AI Integration Implementation | AI Selector Healer Core | Create AI prompt engineering for selector healing | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
4.1 | P4 AI Integration Implementation | AI Selector Healer Core | Add confidence scoring system | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
4.1 | P4 AI Integration Implementation | AI Selector Healer Core | Implement selector validation mechanism | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
4.2 | P4 AI Integration Implementation | AI Configuration and Logging |  | Task | Done | Medium | 8 | 8 | QA Architect (IQ142) |  |  |  |  | Completed pre-baseline (6 sub-tasks)
4.2 | P4 AI Integration Implementation | AI Configuration and Logging | Add AI model configuration to `config.yaml` | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
4.2 | P4 AI Integration Implementation | AI Configuration and Logging | Create `selector_map.json` for historical selector mappings | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
4.2 | P4 AI Integration Implementation | AI Configuration and Logging | Implement `selector_log.json` for AI interaction tracking | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
4.2 | P4 AI Integration Implementation | AI Configuration and Logging | Add AI screenshot capture in `reports/screenshots/ai-*.png` | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
4.2 | P4 AI Integration Implementation | AI Configuration and Logging | Implement AI response parsing and validation | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
4.2 | P4 AI Integration Implementation | AI Configuration and Logging | Add comprehensive AI logging with timestamps | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
4.3 | P4 AI Integration Implementation | AI Integration with Page Objects |  | Task | Done | Medium | 12 | 12 | QA Architect (IQ142) |  |  |  |  | Completed pre-baseline (6 sub-tasks)
4.3 | P4 AI Integration Implementation | AI Integration with Page Objects | Integrate AI healing in `pages/base_page.py` | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
4.3 | P4 AI Integration Implementation | AI Integration with Page Objects | Add AI healing to `fill_input()` method | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
4.3 | P4 AI Integration Implementation | AI Integration with Page Objects | Implement automatic AI trigger on selector failures | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
4.3 | P4 AI Integration Implementation | AI Integration with Page Objects | Add AI context capture (BDD step, page state) | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
4.3 | P4 AI Integration Implementation | AI Integration with Page Objects | Create seamless AI integration with existing POM structure | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
4.3 | P4 AI Integration Implementation | AI Integration with Page Objects | Test AI healing functionality end-to-end | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
4.4 | P4 AI Integration Implementation | AI Documentation and Monitoring |  | Task | Done | Medium | 6 | 6 | QA Architect (IQ142) |  |  |  |  | Completed pre-baseline (6 sub-tasks)
4.4 | P4 AI Integration Implementation | AI Documentation and Monitoring | Update README.md with AI Selector Healing section | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
4.4 | P4 AI Integration Implementation | AI Documentation and Monitoring | Add AI setup instructions and prerequisites | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
4.4 | P4 AI Integration Implementation | AI Documentation and Monitoring | Document AI configuration and usage | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
4.4 | P4 AI Integration Implementation | AI Documentation and Monitoring | Add AI monitoring and log file documentation | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
4.4 | P4 AI Integration Implementation | AI Documentation and Monitoring | Create AI architecture diagrams | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
4.4 | P4 AI Integration Implementation | AI Documentation and Monitoring | Add AI examples and best practices | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
5.1 | P5 Test Implementation | Create Sample Feature Files |  | Task | Done | Medium | 8 | 8 | QA Architect (IQ142) |  |  |  |  | Completed pre-baseline (11 sub-tasks)
5.1 | P5 Test Implementation | Create Sample Feature Files | Create `features/login.feature` | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
5.1 | P5 Test Implementation | Create Sample Feature Files | Create `features/search.feature` | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
5.1 | P5 Test Implementation | Create Sample Feature Files | Create `features/contact.feature` | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
5.1 | P5 Test Implementation | Create Sample Feature Files | Create `features/navigation.feature` | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
5.1 | P5 Test Implementation | Create Sample Feature Files | Create `features/forms.feature` | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
5.1 | P5 Test Implementation | Create Sample Feature Files | Create `features/api_testing.feature` | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
5.1 | P5 Test Implementation | Create Sample Feature Files | Create `features/performance.feature` | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
5.1 | P5 Test Implementation | Create Sample Feature Files | Define various functionality scenarios | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
5.1 | P5 Test Implementation | Create Sample Feature Files | Use proper Gherkin syntax | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
5.1 | P5 Test Implementation | Create Sample Feature Files | Add descriptive scenario names | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
5.1 | P5 Test Implementation | Create Sample Feature Files | Add appropriate tags (@smoke, @regression, @api) | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
5.2 | P5 Test Implementation | Implement Page Object Model (POM) |  | Task | Done | Medium | 12 | 12 | QA Architect (IQ142) |  |  |  |  | Completed pre-baseline (8 sub-tasks)
5.2 | P5 Test Implementation | Implement Page Object Model (POM) | Create `pages/base_page.py` with common functionality | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
5.2 | P5 Test Implementation | Implement Page Object Model (POM) | Create `pages/test_page.py` for main test page | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
5.2 | P5 Test Implementation | Implement Page Object Model (POM) | Create `pages/contact_form_page.py` for form interactions | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
5.2 | P5 Test Implementation | Implement Page Object Model (POM) | Create `pages/page_factory.py` for page object management | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
5.2 | P5 Test Implementation | Implement Page Object Model (POM) | Implement element selectors in page objects | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
5.2 | P5 Test Implementation | Implement Page Object Model (POM) | Add reusable page methods | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
5.2 | P5 Test Implementation | Implement Page Object Model (POM) | Separate page interactions from test logic | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
5.2 | P5 Test Implementation | Implement Page Object Model (POM) | Integrate AI selector healing capabilities | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
5.3 | P5 Test Implementation | Implement Step Definitions |  | Task | Done | Medium | 12 | 12 | QA Architect (IQ142) |  |  |  |  | Completed pre-baseline (12 sub-tasks)
5.3 | P5 Test Implementation | Implement Step Definitions | Create `steps/login_steps.py` | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
5.3 | P5 Test Implementation | Implement Step Definitions | Create `steps/search_steps.py` | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
5.3 | P5 Test Implementation | Implement Step Definitions | Create `steps/contact_steps.py` | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
5.3 | P5 Test Implementation | Implement Step Definitions | Create `steps/navigation_steps.py` | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
5.3 | P5 Test Implementation | Implement Step Definitions | Create `steps/forms_steps.py` | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
5.3 | P5 Test Implementation | Implement Step Definitions | Create `steps/api_steps.py` | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
5.3 | P5 Test Implementation | Implement Step Definitions | Create `steps/performance_steps.py` | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
5.3 | P5 Test Implementation | Implement Step Definitions | Use standard Behave decorators (not BehaveX) | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
5.3 | P5 Test Implementation | Implement Step Definitions | Implement step definitions with Playwright assertions | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
5.3 | P5 Test Implementation | Implement Step Definitions | Add error handling and logging | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
5.3 | P5 Test Implementation | Implement Step Definitions | Remove info-level logs from step files for cleaner output | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
5.3 | P5 Test Implementation | Implement Step Definitions | Keep assertions in step files, not page objects | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
6.1 | P6 Reporting Setup | Install Allure Command Line Tool |  | Task | Done | Medium | 2 | 2 | QA Architect (IQ142) |  |  |  |  | Completed pre-baseline (3 sub-tasks)
6.1 | P6 Reporting Setup | Install Allure Command Line Tool | Install Allure CLI on macOS: `brew install allure` | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
6.1 | P6 Reporting Setup | Install Allure Command Line Tool | Or install on Windows: `scoop install allure` | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
6.1 | P6 Reporting Setup | Install Allure Command Line Tool | Verify Allure installation with `allure --version` | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
6.2 | P6 Reporting Setup | Configure Allure Reporting |  | Task | Done | Medium | 4 | 4 | QA Architect (IQ142) |  |  |  |  | Completed pre-baseline (5 sub-tasks)
6.2 | P6 Reporting Setup | Configure Allure Reporting | Test running tests with Allure formatter | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
6.2 | P6 Reporting Setup | Configure Allure Reporting | Verify report generation | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
6.2 | P6 Reporting Setup | Configure Allure Reporting | Test serving reports locally | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
6.2 | P6 Reporting Setup | Configure Allure Reporting | Implement organized report folder structure | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
6.2 | P6 Reporting Setup | Configure Allure Reporting | Add automatic report folder creation | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
7.1 | P7 Testing and Validation | Basic Test Execution |  | Task | Done | Medium | 4 | 4 | QA Architect (IQ142) |  |  |  |  | Completed pre-baseline (6 sub-tasks)
7.1 | P7 Testing and Validation | Basic Test Execution | Run basic behave command: `behave` | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
7.1 | P7 Testing and Validation | Basic Test Execution | Verify tests execute without errors | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
7.1 | P7 Testing and Validation | Basic Test Execution | Check browser automation works correctly | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
7.1 | P7 Testing and Validation | Basic Test Execution | Validate step definitions are called | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
7.1 | P7 Testing and Validation | Basic Test Execution | Test POM implementation | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
7.1 | P7 Testing and Validation | Basic Test Execution | Test AI selector healing functionality | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
7.2 | P7 Testing and Validation | Tagged Test Execution |  | Task | Done | Medium | 3 | 3 | QA Architect (IQ142) |  |  |  |  | Completed pre-baseline (4 sub-tasks)
7.2 | P7 Testing and Validation | Tagged Test Execution | Add tags to scenarios (e.g., `@smoke`, `@regression`, `@api`) | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
7.2 | P7 Testing and Validation | Tagged Test Execution | Test running specific tagged scenarios | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
7.2 | P7 Testing and Validation | Tagged Test Execution | Verify tag filtering works correctly | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
7.2 | P7 Testing and Validation | Tagged Test Execution | Implement tag support in test runner | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
7.3 | P7 Testing and Validation | Allure Report Validation |  | Task | Done | Medium | 3 | 3 | QA Architect (IQ142) |  |  |  |  | Completed pre-baseline (4 sub-tasks)
7.3 | P7 Testing and Validation | Allure Report Validation | Run tests with Allure formatter | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
7.3 | P7 Testing and Validation | Allure Report Validation | Generate HTML report | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
7.3 | P7 Testing and Validation | Allure Report Validation | Verify report contains test results | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
7.3 | P7 Testing and Validation | Allure Report Validation | Check report styling and navigation | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
7.4 | P7 Testing and Validation | AI Selector Healing Validation |  | Task | Done | Medium | 6 | 6 | QA Architect (IQ142) |  |  |  |  | Completed pre-baseline (6 sub-tasks)
7.4 | P7 Testing and Validation | AI Selector Healing Validation | Test AI healing with failing selectors | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
7.4 | P7 Testing and Validation | AI Selector Healing Validation | Verify AI screenshot capture functionality | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
7.4 | P7 Testing and Validation | AI Selector Healing Validation | Validate AI selector suggestions | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
7.4 | P7 Testing and Validation | AI Selector Healing Validation | Test AI confidence scoring | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
7.4 | P7 Testing and Validation | AI Selector Healing Validation | Verify selector mapping persistence | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
7.4 | P7 Testing and Validation | AI Selector Healing Validation | Test AI log generation and monitoring | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
8.1 | P8 Advanced Features | Multiple Browser Support |  | Task | Done | Medium | 6 | 6 | QA Architect (IQ142) |  |  |  |  | Completed pre-baseline (5 sub-tasks)
8.1 | P8 Advanced Features | Multiple Browser Support | Extend browser setup to support multiple browsers | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
8.1 | P8 Advanced Features | Multiple Browser Support | Add configuration for Chrome, Firefox, Safari | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
8.1 | P8 Advanced Features | Multiple Browser Support | Implement browser selection logic | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
8.1 | P8 Advanced Features | Multiple Browser Support | Test cross-browser compatibility | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
8.1 | P8 Advanced Features | Multiple Browser Support | Add browser selection via command line arguments | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
8.2 | P8 Advanced Features | Headless Mode Support |  | Task | Done | Medium | 5 | 5 | QA Architect (IQ142) |  |  |  |  | Completed pre-baseline (7 sub-tasks)
8.2 | P8 Advanced Features | Headless Mode Support | Implement flexible headless mode configuration | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
8.2 | P8 Advanced Features | Headless Mode Support | Add environment variable support (HEADLESS) | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
8.2 | P8 Advanced Features | Headless Mode Support | Create command-line runner with headless options | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
8.2 | P8 Advanced Features | Headless Mode Support | Support headless mode in parallel execution | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
8.2 | P8 Advanced Features | Headless Mode Support | Add browser selection with headless mode | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
8.2 | P8 Advanced Features | Headless Mode Support | Test headless mode functionality | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
8.2 | P8 Advanced Features | Headless Mode Support | Remove headless mode from config file (command line only) | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
8.3 | P8 Advanced Features | Screenshot and Logging |  | Task | Done | Medium | 5 | 5 | QA Architect (IQ142) |  |  |  |  | Completed pre-baseline (6 sub-tasks)
8.3 | P8 Advanced Features | Screenshot and Logging | Implement screenshot capture on failure | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
8.3 | P8 Advanced Features | Screenshot and Logging | Add logging functionality | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
8.3 | P8 Advanced Features | Screenshot and Logging | Configure log levels and output | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
8.3 | P8 Advanced Features | Screenshot and Logging | Test failure scenarios with screenshots | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
8.3 | P8 Advanced Features | Screenshot and Logging | Create organized screenshot folder structure | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
8.3 | P8 Advanced Features | Screenshot and Logging | Add AI-specific screenshot capture | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
8.4 | P8 Advanced Features | Parallel Execution |  | Task | Done | Medium | 16 | 16 | QA Architect (IQ142) |  |  |  |  | Completed pre-baseline (12 sub-tasks)
8.4 | P8 Advanced Features | Parallel Execution | Research parallel execution options | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
8.4 | P8 Advanced Features | Parallel Execution | Implement custom parallel execution with multiprocessing | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
8.4 | P8 Advanced Features | Parallel Execution | Integrate parallel execution into run_tests.py | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
8.4 | P8 Advanced Features | Parallel Execution | Add worker count configuration (--workers option) | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
8.4 | P8 Advanced Features | Parallel Execution | Implement report combining from multiple workers | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
8.4 | P8 Advanced Features | Parallel Execution | Test performance improvements | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
8.4 | P8 Advanced Features | Parallel Execution | Remove separate parallel_runner.py (integrated into run_tests.py) | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
8.4 | P8 Advanced Features | Parallel Execution | Add live streaming console output | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
8.4 | P8 Advanced Features | Parallel Execution | Filter empty lines and "Using selector" messages | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
8.4 | P8 Advanced Features | Parallel Execution | Ensure report folders are created only once | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
8.4 | P8 Advanced Features | Parallel Execution | Add tag filtering support in parallel mode | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
8.4 | P8 Advanced Features | Parallel Execution | Optimize worker count based on feature files | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
8.5 | P8 Advanced Features | Configuration Management |  | Task | Done | Medium | 6 | 6 | QA Architect (IQ142) |  |  |  |  | Completed pre-baseline (8 sub-tasks)
8.5 | P8 Advanced Features | Configuration Management | Implement YAML-based configuration system | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
8.5 | P8 Advanced Features | Configuration Management | Create `config.yaml` for base URL configuration | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
8.5 | P8 Advanced Features | Configuration Management | Add helper functions to build URLs with paths | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
8.5 | P8 Advanced Features | Configuration Management | Remove browser and headless configuration from config file | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
8.5 | P8 Advanced Features | Configuration Management | Keep browser and headless mode via command line only | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
8.5 | P8 Advanced Features | Configuration Management | Test configuration loading and URL building | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
8.5 | P8 Advanced Features | Configuration Management | Create basic framework constants system | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
8.5 | P8 Advanced Features | Configuration Management | Add AI model configuration to config.yaml | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
8.6 | P8 Advanced Features | Test Runner Enhancements |  | Task | Done | Medium | 10 | 10 | QA Architect (IQ142) |  |  |  |  | Completed pre-baseline (10 sub-tasks)
8.6 | P8 Advanced Features | Test Runner Enhancements | Create comprehensive test runner script (`run_tests.py`) | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
8.6 | P8 Advanced Features | Test Runner Enhancements | Add command-line argument parsing | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
8.6 | P8 Advanced Features | Test Runner Enhancements | Support sequential and parallel execution modes | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
8.6 | P8 Advanced Features | Test Runner Enhancements | Add browser and headless mode options | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
8.6 | P8 Advanced Features | Test Runner Enhancements | Implement tag filtering support | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
8.6 | P8 Advanced Features | Test Runner Enhancements | Add feature file selection support | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
8.6 | P8 Advanced Features | Test Runner Enhancements | Create organized report structure | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
8.6 | P8 Advanced Features | Test Runner Enhancements | Add failing scenarios capture and display | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
8.6 | P8 Advanced Features | Test Runner Enhancements | Implement output filtering for cleaner console output | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
8.6 | P8 Advanced Features | Test Runner Enhancements | Add accurate worker count display | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
8.7 | P8 Advanced Features | Playwright Tracing |  | Task | Done | Medium | 16 | 16 | QA Architect (IQ142) |  |  |  |  | Completed pre-baseline (11 sub-tasks)
8.7 | P8 Advanced Features | Playwright Tracing | Design tracing architecture and requirements | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
8.7 | P8 Advanced Features | Playwright Tracing | Plan integration points for trace management | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
8.7 | P8 Advanced Features | Playwright Tracing | Define trace file structure and organization | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
8.7 | P8 Advanced Features | Playwright Tracing | Implement browser setup with tracing support | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
8.7 | P8 Advanced Features | Playwright Tracing | Create trace manager utility class | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
8.7 | P8 Advanced Features | Playwright Tracing | Add tracing command-line options | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
8.7 | P8 Advanced Features | Playwright Tracing | Integrate tracing with environment hooks | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
8.7 | P8 Advanced Features | Playwright Tracing | Add trace file cleanup and archiving | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
8.7 | P8 Advanced Features | Playwright Tracing | Implement trace summary reporting | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
8.7 | P8 Advanced Features | Playwright Tracing | Add trace integration with Allure reports | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
8.7 | P8 Advanced Features | Playwright Tracing | Test tracing functionality end-to-end | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
9.1 | P9 CI/CD Integration | GitHub Actions Setup |  | Task | Not start | Medium | 24 | 0 | DevOps Engineer | 9.5 |  | 2026-07-23 | 2026-07-30 | Secondary CI; reuse 9.5 scripts; Slack/email notifications
9.1 | P9 CI/CD Integration | GitHub Actions Setup | Create `.github/workflows/` directory | Sub-task | Not start | Medium |  |  | DevOps Engineer
9.1 | P9 CI/CD Integration | GitHub Actions Setup | Create main test workflow (`test-runner.yml`) | Sub-task | Not start | Medium |  |  | DevOps Engineer
9.1 | P9 CI/CD Integration | GitHub Actions Setup | Create scheduled tests workflow (`scheduled-tests.yml`) | Sub-task | Not start | Medium |  |  | DevOps Engineer
9.1 | P9 CI/CD Integration | GitHub Actions Setup | Create pull request validation workflow (`pull-request.yml`) | Sub-task | Not start | Medium |  |  | DevOps Engineer
9.1 | P9 CI/CD Integration | GitHub Actions Setup | Configure test execution steps | Sub-task | Not start | Medium |  |  | DevOps Engineer
9.1 | P9 CI/CD Integration | GitHub Actions Setup | Add Allure report publishing | Sub-task | Not start | Medium |  |  | DevOps Engineer
9.1 | P9 CI/CD Integration | GitHub Actions Setup | Add Slack/email notifications | Sub-task | Not start | Medium |  |  | DevOps Engineer
9.1 | P9 CI/CD Integration | GitHub Actions Setup | Test CI/CD pipeline | Sub-task | Not start | Medium |  |  | DevOps Engineer
9.2 | P9 CI/CD Integration | GitLab CI Setup |  | Task | Not start | High | 20 | 0 | DevOps Engineer | 9.5 |  | 2026-07-16 | 2026-07-22 | Primary CI target (GitLab stack); includes Pages report hosting
9.2 | P9 CI/CD Integration | GitLab CI Setup | Create `.gitlab-ci.yml` file | Sub-task | Not start | High |  |  | DevOps Engineer
9.2 | P9 CI/CD Integration | GitLab CI Setup | Configure test stages (setup, test, report, deploy) | Sub-task | Not start | High |  |  | DevOps Engineer
9.2 | P9 CI/CD Integration | GitLab CI Setup | Add multi-browser testing matrix | Sub-task | Not start | High |  |  | DevOps Engineer
9.2 | P9 CI/CD Integration | GitLab CI Setup | Add report artifacts | Sub-task | Not start | High |  |  | DevOps Engineer
9.2 | P9 CI/CD Integration | GitLab CI Setup | Configure GitLab Pages for report hosting | Sub-task | Not start | High |  |  | DevOps Engineer
9.2 | P9 CI/CD Integration | GitLab CI Setup | Test GitLab CI pipeline | Sub-task | Not start | High |  |  | DevOps Engineer
9.3 | P9 CI/CD Integration | Jenkins Integration |  | Task | Not start | Low | 14 | 0 | DevOps Engineer | 9.5 |  | 2026-07-31 | 2026-08-04 | Optional provider; descope if no Jenkins infra (risk R2)
9.3 | P9 CI/CD Integration | Jenkins Integration | Create `Jenkinsfile` for pipeline | Sub-task | Not start | Low |  |  | DevOps Engineer
9.3 | P9 CI/CD Integration | Jenkins Integration | Configure multi-stage pipeline | Sub-task | Not start | Low |  |  | DevOps Engineer
9.3 | P9 CI/CD Integration | Jenkins Integration | Add HTML report publishing | Sub-task | Not start | Low |  |  | DevOps Engineer
9.3 | P9 CI/CD Integration | Jenkins Integration | Configure workspace cleanup | Sub-task | Not start | Low |  |  | DevOps Engineer
9.3 | P9 CI/CD Integration | Jenkins Integration | Test Jenkins pipeline | Sub-task | Not start | Low |  |  | DevOps Engineer
9.5 | P9 CI/CD Integration | CI/CD Scripts |  | Task | Not start | High | 13 | 0 | DevOps Engineer | 8.7 | 9.2;9.1;9.3 | 2026-07-13 | 2026-07-15 | Shared scripts are prerequisite for all CI providers
9.5 | P9 CI/CD Integration | CI/CD Scripts | Create environment setup script | Sub-task | Not start | High |  |  | DevOps Engineer
9.5 | P9 CI/CD Integration | CI/CD Scripts | Create test execution script | Sub-task | Not start | High |  |  | DevOps Engineer
9.5 | P9 CI/CD Integration | CI/CD Scripts | Create report publishing script | Sub-task | Not start | High |  |  | DevOps Engineer
9.5 | P9 CI/CD Integration | CI/CD Scripts | Create cleanup scripts | Sub-task | Not start | High |  |  | DevOps Engineer
9.5 | P9 CI/CD Integration | CI/CD Scripts | Test all CI/CD scripts | Sub-task | Not start | High |  |  | DevOps Engineer
10.1 | P10 Documentation | Update README |  | Task | Done | Medium | 6 | 6 | QA Architect (IQ142) |  |  |  |  | Completed pre-baseline (12 sub-tasks)
10.1 | P10 Documentation | Update README | Verify all setup instructions are accurate | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
10.1 | P10 Documentation | Update README | Add troubleshooting section | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
10.1 | P10 Documentation | Update README | Include common issues and solutions | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
10.1 | P10 Documentation | Update README | Add contribution guidelines | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
10.1 | P10 Documentation | Update README | Document all command-line options | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
10.1 | P10 Documentation | Update README | Add examples for all features | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
10.1 | P10 Documentation | Update README | Update to reflect POM implementation | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
10.1 | P10 Documentation | Update README | Remove BehaveX references | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
10.1 | P10 Documentation | Update README | Add AI Selector Healing documentation | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
10.1 | P10 Documentation | Update README | Include AI setup and configuration | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
10.1 | P10 Documentation | Update README | Add AI monitoring and logs section | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
10.1 | P10 Documentation | Update README | Update architecture diagram with AI components | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
10.2 | P10 Documentation | Create Additional Documentation |  | Task | Done | Medium | 4 | 4 | QA Architect (IQ142) |  |  |  |  | Completed pre-baseline (6 sub-tasks)
10.2 | P10 Documentation | Create Additional Documentation | Create comprehensive TASKS.md | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
10.2 | P10 Documentation | Create Additional Documentation | Document all implemented features | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
10.2 | P10 Documentation | Create Additional Documentation | Add troubleshooting guide | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
10.2 | P10 Documentation | Create Additional Documentation | Document best practices | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
10.2 | P10 Documentation | Create Additional Documentation | Update to reflect current state | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
10.2 | P10 Documentation | Create Additional Documentation | Add AI integration documentation | Sub-task | Done | Medium |  |  | QA Architect (IQ142)
11.1 | P11 AI-Driven Enhancements (Proposed) | Full-Coverage AI Self-Healing |  | Task | Not start | High | 24 | 0 | QA Architect (IQ142) | M1 | 11.2;11.6 | 2026-08-05 | 2026-08-12 | Extend self-healing beyond fill_input to click/select/hover/assert
11.1 | P11 AI-Driven Enhancements (Proposed) | Full-Coverage AI Self-Healing | Refactor healing into interceptor at base_page action layer | Sub-task | Not start | High |  |  | QA Architect (IQ142)
11.1 | P11 AI-Driven Enhancements (Proposed) | Full-Coverage AI Self-Healing | Add healing to click/select/hover/check/assert locators | Sub-task | Not start | High |  |  | QA Architect (IQ142)
11.1 | P11 AI-Driven Enhancements (Proposed) | Full-Coverage AI Self-Healing | Add healing telemetry per action type | Sub-task | Not start | High |  |  | QA Architect (IQ142)
11.1 | P11 AI-Driven Enhancements (Proposed) | Full-Coverage AI Self-Healing | Regression-test healing across all 7 feature files | Sub-task | Not start | High |  |  | QA Architect (IQ142)
11.2 | P11 AI-Driven Enhancements (Proposed) | Multi-Model AI Support & Cost Guardrails |  | Task | Not start | High | 20 | 0 | QA Architect (IQ142) | 11.1 | 11.3;11.4 | 2026-08-13 | 2026-08-19 | Ollama local + cloud API fallback; cost guardrails, model routing
11.2 | P11 AI-Driven Enhancements (Proposed) | Multi-Model AI Support & Cost Guardrails | Abstract model provider interface (Ollama, Claude API, others) | Sub-task | Not start | High |  |  | QA Architect (IQ142)
11.2 | P11 AI-Driven Enhancements (Proposed) | Multi-Model AI Support & Cost Guardrails | Route cheap tasks to small local model, reasoning to larger model | Sub-task | Not start | High |  |  | QA Architect (IQ142)
11.2 | P11 AI-Driven Enhancements (Proposed) | Multi-Model AI Support & Cost Guardrails | Add token/cost budget guardrails and rule-based fallback | Sub-task | Not start | High |  |  | QA Architect (IQ142)
11.2 | P11 AI-Driven Enhancements (Proposed) | Multi-Model AI Support & Cost Guardrails | Add offline mode for deterministic CI runs | Sub-task | Not start | High |  |  | QA Architect (IQ142)
11.3 | P11 AI-Driven Enhancements (Proposed) | AI Test Generation (Requirements-to-Gherkin) |  | Task | Not start | High | 32 | 0 | QA Architect (IQ142) | 11.2 | 11.9 | 2026-08-20 | 2026-08-31 | LLM: Jira/requirements -> Gherkin drafts with human review gate
11.3 | P11 AI-Driven Enhancements (Proposed) | AI Test Generation (Requirements-to-Gherkin) | Design prompt templates and TestSpec-style schema for scenarios | Sub-task | Not start | High |  |  | QA Architect (IQ142)
11.3 | P11 AI-Driven Enhancements (Proposed) | AI Test Generation (Requirements-to-Gherkin) | Ingest Jira stories / acceptance criteria | Sub-task | Not start | High |  |  | QA Architect (IQ142)
11.3 | P11 AI-Driven Enhancements (Proposed) | AI Test Generation (Requirements-to-Gherkin) | Generate Gherkin drafts + step stubs | Sub-task | Not start | High |  |  | QA Architect (IQ142)
11.3 | P11 AI-Driven Enhancements (Proposed) | AI Test Generation (Requirements-to-Gherkin) | Human review gate and duplicate-scenario detection | Sub-task | Not start | High |  |  | QA Architect (IQ142)
11.3 | P11 AI-Driven Enhancements (Proposed) | AI Test Generation (Requirements-to-Gherkin) | Pilot on one epic; measure authoring time saved | Sub-task | Not start | High |  |  | QA Architect (IQ142)
11.4 | P11 AI-Driven Enhancements (Proposed) | AI Failure Triage & Root-Cause Analysis |  | Task | Not start | High | 24 | 0 | SDET | 11.2 | 11.8 | 2026-09-01 | 2026-09-08 | AI failure triage / RCA summaries attached to Allure results
11.4 | P11 AI-Driven Enhancements (Proposed) | AI Failure Triage & Root-Cause Analysis | Collect failure context (trace, screenshot, DOM, logs) | Sub-task | Not start | High |  |  | SDET
11.4 | P11 AI-Driven Enhancements (Proposed) | AI Failure Triage & Root-Cause Analysis | Classify failure type (app bug / test bug / env / flaky) | Sub-task | Not start | High |  |  | SDET
11.4 | P11 AI-Driven Enhancements (Proposed) | AI Failure Triage & Root-Cause Analysis | Generate RCA summary attached to Allure | Sub-task | Not start | High |  |  | SDET
11.4 | P11 AI-Driven Enhancements (Proposed) | AI Failure Triage & Root-Cause Analysis | Auto-suggest fix for test-side failures | Sub-task | Not start | High |  |  | SDET
11.5 | P11 AI-Driven Enhancements (Proposed) | Flaky-Test Prediction & Analytics |  | Task | Not start | Medium | 20 | 0 | SDET | M1 | 11.8 | 2026-09-15 | 2026-09-21 | Flaky-test prediction from CI history (needs pipeline data)
11.5 | P11 AI-Driven Enhancements (Proposed) | Flaky-Test Prediction & Analytics | Persist CI run history to results store | Sub-task | Not start | Medium |  |  | SDET
11.5 | P11 AI-Driven Enhancements (Proposed) | Flaky-Test Prediction & Analytics | Compute flakiness score per scenario | Sub-task | Not start | Medium |  |  | SDET
11.5 | P11 AI-Driven Enhancements (Proposed) | Flaky-Test Prediction & Analytics | Quarantine workflow for flaky tags | Sub-task | Not start | Medium |  |  | SDET
11.5 | P11 AI-Driven Enhancements (Proposed) | Flaky-Test Prediction & Analytics | Trend report in dashboard | Sub-task | Not start | Medium |  |  | SDET
11.6 | P11 AI-Driven Enhancements (Proposed) | RAG Selector Knowledge Base |  | Task | Not start | Medium | 16 | 0 | QA Architect (IQ142) | 11.1 |  | 2026-09-09 | 2026-09-14 | selector_map.json -> embedded/RAG selector knowledge base
11.6 | P11 AI-Driven Enhancements (Proposed) | RAG Selector Knowledge Base | Embed historical selector_map.json entries | Sub-task | Not start | Medium |  |  | QA Architect (IQ142)
11.6 | P11 AI-Driven Enhancements (Proposed) | RAG Selector Knowledge Base | Retrieve similar past healings as few-shot context | Sub-task | Not start | Medium |  |  | QA Architect (IQ142)
11.6 | P11 AI-Driven Enhancements (Proposed) | RAG Selector Knowledge Base | Measure healing confidence uplift | Sub-task | Not start | Medium |  |  | QA Architect (IQ142)
11.7 | P11 AI-Driven Enhancements (Proposed) | AI-Assisted Visual Regression |  | Task | Not start | Medium | 24 | 0 | SDET | M2 |  | 2026-09-28 | 2026-10-05 | AI-assisted visual regression (baseline diff + semantic filter)
11.7 | P11 AI-Driven Enhancements (Proposed) | AI-Assisted Visual Regression | Baseline screenshot management | Sub-task | Not start | Medium |  |  | SDET
11.7 | P11 AI-Driven Enhancements (Proposed) | AI-Assisted Visual Regression | Pixel diff + AI semantic filter to cut false positives | Sub-task | Not start | Medium |  |  | SDET
11.7 | P11 AI-Driven Enhancements (Proposed) | AI-Assisted Visual Regression | Allure integration for visual diffs | Sub-task | Not start | Medium |  |  | SDET
11.8 | P11 AI-Driven Enhancements (Proposed) | AI Analytics Dashboard |  | Task | Not start | Medium | 16 | 0 | SDET | 11.4;11.5 |  | 2026-09-22 | 2026-09-25 | AI analytics dashboard: healing rate, confidence trend, cost
11.8 | P11 AI-Driven Enhancements (Proposed) | AI Analytics Dashboard | Healing success rate & confidence trend | Sub-task | Not start | Medium |  |  | SDET
11.8 | P11 AI-Driven Enhancements (Proposed) | AI Analytics Dashboard | AI cost per run / per healed selector | Sub-task | Not start | Medium |  |  | SDET
11.8 | P11 AI-Driven Enhancements (Proposed) | AI Analytics Dashboard | Triage accuracy metrics | Sub-task | Not start | Medium |  |  | SDET
11.9 | P11 AI-Driven Enhancements (Proposed) | AI Test Data Management |  | Task | Not start | Low | 20 | 0 | SDET | 11.3 |  | 2026-10-12 | 2026-10-16 | AI synthetic test data generation + data management layer
11.9 | P11 AI-Driven Enhancements (Proposed) | AI Test Data Management | Schema-aware synthetic data generation | Sub-task | Not start | Low |  |  | SDET
11.9 | P11 AI-Driven Enhancements (Proposed) | AI Test Data Management | Data lifecycle (seed/teardown) utilities | Sub-task | Not start | Low |  |  | SDET
11.9 | P11 AI-Driven Enhancements (Proposed) | AI Test Data Management | PII-safe masking rules | Sub-task | Not start | Low |  |  | SDET
11.10 | P11 AI-Driven Enhancements (Proposed) | Test Management Integration (TestRail/Jira) |  | Task | Not start | Medium | 16 | 0 | QA Architect (IQ142) | M1 |  | 2026-10-06 | 2026-10-09 | TestRail/Jira sync with AI result-to-case mapping
11.10 | P11 AI-Driven Enhancements (Proposed) | Test Management Integration (TestRail/Jira) | Push results to TestRail via API | Sub-task | Not start | Medium |  |  | QA Architect (IQ142)
11.10 | P11 AI-Driven Enhancements (Proposed) | Test Management Integration (TestRail/Jira) | AI mapping of scenarios to existing cases | Sub-task | Not start | Medium |  |  | QA Architect (IQ142)
11.10 | P11 AI-Driven Enhancements (Proposed) | Test Management Integration (TestRail/Jira) | Jira defect drafting from RCA output | Sub-task | Not start | Medium |  |  | QA Architect (IQ142)

## Gantt
Gantt - Remaining Work (Jul-Oct 2026)
Weekly grid; bars = scheduled task duration, diamond = milestone. Colors: High=red, Medium=blue, Low=grey.
Week commencing
ID | Task / Milestone | Priority | PIC | Est (h) | Start | End | 2026-07-13 | 2026-07-20 | 2026-07-27 | 2026-08-03 | 2026-08-10 | 2026-08-17 | 2026-08-24 | 2026-08-31 | 2026-09-07 | 2026-09-14 | 2026-09-21 | 2026-09-28 | 2026-10-05 | 2026-10-12 | 2026-10-19
PHASE 9 - CI/CD INTEGRATION
9.5 | CI/CD Scripts | High | DevOps Engineer | 13 | 2026-07-13 | 2026-07-15 | ██
9.2 | GitLab CI Setup | High | DevOps Engineer | 20 | 2026-07-16 | 2026-07-22 | ██ | ██
9.1 | GitHub Actions Setup | Medium | DevOps Engineer | 24 | 2026-07-23 | 2026-07-30 |  | ██ | ██
9.3 | Jenkins Integration | Low | DevOps Engineer | 14 | 2026-07-31 | 2026-08-04 |  |  | ██ | ██
M1 | CI/CD Live (GitLab primary, all providers green) |  |  |  | 2026-08-04 | 2026-08-04 |  |  |  | ◆
PHASE 11 - AI-DRIVEN ENHANCEMENTS (PROPOSED)
11.1 | Full-Coverage AI Self-Healing | High | QA Architect (IQ142) | 24 | 2026-08-05 | 2026-08-12 |  |  |  | ██ | ██
11.2 | Multi-Model AI Support & Cost Guardrails | High | QA Architect (IQ142) | 20 | 2026-08-13 | 2026-08-19 |  |  |  |  | ██ | ██
11.3 | AI Test Generation (Requirements-to-Gherkin) | High | QA Architect (IQ142) | 32 | 2026-08-20 | 2026-08-31 | [5 empty] | ██ | ██ | ██
11.4 | AI Failure Triage & Root-Cause Analysis | High | SDET | 24 | 2026-09-01 | 2026-09-08 | [7 empty] | ██ | ██
M2 | AI v2 Core Complete (healing v2, multi-model, gen, triage) |  |  |  | 2026-09-08 | 2026-09-08 | [8 empty] | ◆
11.6 | RAG Selector Knowledge Base | Medium | QA Architect (IQ142) | 16 | 2026-09-09 | 2026-09-14 | [8 empty] | ██ | ██
11.5 | Flaky-Test Prediction & Analytics | Medium | SDET | 20 | 2026-09-15 | 2026-09-21 | [9 empty] | ██ | ██
11.8 | AI Analytics Dashboard | Medium | SDET | 16 | 2026-09-22 | 2026-09-25 | [10 empty] | ██
M3 | AI Analytics & Quality Insights Live |  |  |  | 2026-09-25 | 2026-09-25 | [10 empty] | ◆
11.7 | AI-Assisted Visual Regression | Medium | SDET | 24 | 2026-09-28 | 2026-10-05 | [11 empty] | ██ | ██
11.10 | Test Management Integration (TestRail/Jira) | Medium | QA Architect (IQ142) | 16 | 2026-10-06 | 2026-10-09 | [12 empty] | ██
11.9 | AI Test Data Management | Low | SDET | 20 | 2026-10-12 | 2026-10-16 | [13 empty] | ██
M4 | Framework v2.0 GA |  |  |  | 2026-10-16 | 2026-10-16 | [13 empty] | ◆

## Milestones
Milestone Tracker
ID | Milestone | Target Date | Gate Criteria (tasks Done) | Status | Days to Target (from baseline)
ID | Milestone | Target Date | Gate Criteria (tasks Done) | Status | Days to Target (from baseline)
M1 | CI/CD Live (GitLab primary, all providers green) | 2026-08-04 | 9.2, 9.1, 9.3, 9.5 | Not start | 22
M2 | AI v2 Core Complete (healing v2, multi-model, gen, triage) | 2026-09-08 | 11.1, 11.2, 11.3, 11.4 | Not start | 57
M3 | AI Analytics & Quality Insights Live | 2026-09-25 | 11.5, 11.6, 11.8 | Not start | 74
M4 | Framework v2.0 GA | 2026-10-16 | 11.7, 11.9, 11.10 | Not start | 95

## AI Enhancements
AI-Driven Enhancement Recommendations
Architect assessment of the current Playwright+Behave+Allure framework; mapped to Phase 11 plan tasks.
# | Enhancement | Current-State Gap | Recommendation | Value / KPI | Risk & Mitigation | Priority | Plan Task
1 | Full-coverage self-healing | Healing wired only into fill_input(); clicks/selects/asserts still fail hard | Move healing into a locator interceptor at the base-page action layer so every interaction is covered | Cut selector-related failures >70%; KPI: healed-action rate per run | Silent wrong-element healing -> require confidence >=90% + post-heal assertion | High | 11.1
2 | Multi-model routing + cost control | Single hardcoded Ollama devstral:24b; no fallback, no budget | Provider abstraction: small local model for cheap tasks, larger model for reasoning; rule-based fallback first; token budget per run | 30-60% AI cost reduction; deterministic CI stays offline | Model drift -> pin versions, golden-prompt regression suite | High | 11.2
3 | AI test generation | Scenarios authored fully manually | Jira story -> Gherkin draft + step stubs with mandatory human review and duplicate detection | 40%+ authoring time saved; KPI: accepted-draft rate | Low-quality drafts -> review gate, style lint on generated Gherkin | High | 11.3
4 | AI failure triage / RCA | Failures need manual trace/screenshot analysis | Classify failures (app/test/env/flaky) and attach AI RCA summary to Allure | 50% faster triage; KPI: triage accuracy vs human label | Wrong classification -> show evidence, keep human override | High | 11.4
5 | Flaky-test analytics | No CI history; flakiness invisible | Persist run history, flakiness score, quarantine workflow | Stable signal to devs; KPI: flake rate, MTTR | Needs CI live first (depends on M1) | Medium | 11.5
6 | RAG selector memory | selector_map.json is exact-match only | Embed past healings; retrieve similar cases as few-shot context for the healer | Higher healing confidence, fewer LLM calls | Stale embeddings -> refresh on selector churn | Medium | 11.6
7 | AI visual regression | No visual testing (open backlog item) | Baseline diff + AI semantic filter to suppress trivial-pixel noise | Catch UI regressions Playwright asserts miss | False positives -> semantic filter + per-component masks | Medium | 11.7
8 | AI analytics dashboard | 95% confidence is self-reported, not measured over time | Dashboard: healing success rate, confidence trend, AI cost, triage accuracy | Evidence-based AI ROI reporting to leadership | None significant | Medium | 11.8
9 | AI test data management | No data-driven testing (open backlog item) | Schema-aware synthetic data with PII-safe masking; seed/teardown utilities | Unblocks data-driven suites safely | Invalid data -> schema validation before use | Low | 11.9
10 | Test-management integration | No TestRail/Jira sync (open backlog item) | Push results to TestRail; AI maps scenarios to cases; draft Jira defects from RCA | Single source of truth for QA status | API limits -> batch sync | Medium | 11.10